## Cover
Atlas — New Windows Server Commissioning
GOLDEN MASTER TEMPLATE — the reusable shell every new Windows Server 2025 member server (Tier 1) is commissioned from. Copy this file per host, then fill the copy; leave this master blank. The Linux-server and per-service checklists are built from this same shape.
Host identity (fill the yellow cells)
Hostname |  | e.g. FS01
Role / purpose |  | e.g. file & print server
Tier |  | Tier 1 (member server)
IPv4 / mask / gateway |  | from IP-Addressing-Plan-VLSM
VLAN |  | role VLAN
AD OU |  | Computers\Servers\<type>
Hypervisor |  | PVE01 (R410) / PVE02 (EQR6)
OS build |  | Windows Server 2025 (build)
Commissioned by
Start date
Completion date
Progress
Steps complete |  | live count from the Checklist tab
Legend & rules
✅ device-verified | a command + its read-back exists (POL-0001)
🟡 authored / operator-reported | not yet verified on the box
📋 planned / gated | not started, or waiting on a dependency
🔴 blocker / trap | must-do / must-not-miss
Yellow cells | the only cells you fill in (Done✓ · Date · Who · Time · Notes)
POL-0002 — no live secrets | local-admin/LAPS/DSRM passwords live in Vaultwarden; note WHERE, not what
Read more — in-repo references (no internet needed)
Phase | Owner doc(s) in the repo | What it owns
0 Prereqs | IP-Addressing-Plan-VLSM · Service-Server-Build-Plan | addressing, host placement & VM sizing
1 VM & OS | DC-Domain-Controllers/Build-Guide (Stage 1) · Playbooks/Proxmox-Inspect-and-Troubleshoot | base Windows build; VirtIO/guest-agent on Proxmox
2 Base config | 303-Windows-Design-Standards · ADR-0020 (time) | naming, DNS→DCs, timezone, licensing
3 Time & net | ADR-0020 · Playbooks/Trace-a-Blocked-Flow · Recover-from-a-DNS-Outage | DOMHIER time trap; connectivity & DNS checks
4 Hardening | 303 Part 6 · GPO-Design-and-Build | firewall, legacy-protocol off, RDP/NLA, baseline
5 Domain join | DC-Domain-Controllers/Build-Guide (Stage 8) · 303 Part 3 · ADR-0024 | join, Servers OU, tiered admin, LAPS
6 Telemetry | MON01 device page · WSUS01 · BKP01 · ADR-0013 · DC Build-Guide (Stage 9) | logging/SNMP, updates, backup, machine cert
7 Record | Templates/Build-Record-Template · NETBOX01 device page | evidence capture & source-of-truth entry
If a step fails — related Playbooks & Runbooks
Playbooks are the reciprocal of this checklist: a Playbook step may say “check the commissioning checklist for this item,” and the rows below point back into the Playbooks when a step won’t pass. (Runbooks — the automated equivalents — arrive with the automation work, ADR-0048.)
A member server won’t join atlas.lab |  | Playbooks/Domain-Join-Fails.md
VM won’t boot / no NIC / bad clock on Proxmox |  | Playbooks/Proxmox-Inspect-and-Troubleshoot.md
A network path is blocked (join/DNS/telemetry fails) |  | Playbooks/Trace-a-Blocked-Flow.md
Name resolution fails (join or gpupdate errors) |  | Playbooks/Recover-from-a-DNS-Outage.md
Prove a specific host↔service connection |  | Playbooks/Test-a-Connection.md
Sign-off
Builder — name / date
Reviewer — name / date
Read-backs pasted into Devices/<host>/Build-Record? |  | Y / N
Host added to NetBox? |  | Y / N / n/a (NetBox pending)

## Checklist
Atlas — New Windows Server Commissioning Checklist
Host: _____________ · Role: _____________ · Lab-02-Cisco-Core · Windows Server 2025 member server (Tier 1). Golden master — copy per server; fill the yellow cells. See the Cover tab for identity, references & sign-off.
Source: 303-Windows-Design-Standards + DC-Domain-Controllers/Build-Guide (Stage-1 base) + 302 build roadmap · aligned to CIS Microsoft Windows Server Benchmark + Microsoft Security Baselines (SCT) · format model: PVE02 commissioning xlsx (#33).
HOW TO USE ▶ Copy this file per new server. Fill the yellow cells: Done (✓) · Date · Who · Time · Notes/Evidence (📸). Work top-to-bottom — the 🔴 Phase-0 gate must be fully checked before you install. The Ref column points to the in-repo doc to read (no internet needed).
Row 9 (grey) is an EXAMPLE showing the expected format — overwrite or delete it. Never record a live secret (POL-0002): local-admin/LAPS/DSRM passwords live in Vaultwarden — note where, not what.
Steps complete:
Phase | # | Task | What to do | Verify (command) | Expected (healthy) | Ref (in-repo) | Done ✓ | Date | Who | Time | Notes / Evidence (📸)
2 · Base OS configuration | — | (example) Set the static IPv4 | overwrite or delete this row | Get-NetIPConfiguration | IP matches the plan | IP-Addressing-Plan-VLSM | ✓ | 2026-08-05 | seth | 14:20 | 10.40.0.x/26 set; 📸 ipconfig.png
0 · Prerequisites gate (🔴 do not proceed until all checked) | 1 | Reserve IP & confirm sizing | Assign the host's static IP from IP-Addressing-Plan-VLSM (correct role VLAN) + RAM/vCPU/disk from Service-Server-Build-Plan. | (doc) IP-Addressing-Plan-VLSM ; Service-Server-Build-Plan | IP + sizing assigned; no conflict | IP-Addressing-Plan-VLSM · Service-Server-Build-Plan
| 2 | VLAN / trunk ready end-to-end | vNIC tagged to the role VLAN; the PVE bridge carries it; the SW01 uplink trunk allows it. | (SW01) show interfaces trunk ; (PVE) bridge vlan show | role VLAN tagged host→switch | SW01 page-set · PVE01-Networking (ADR-0034)
| 3 | DCs reachable (DNS + LDAP) | DC01 10.20.0.2 / DC02 10.20.0.3 online; atlas.lab resolves. | Test-NetConnection 10.20.0.2 -Port 389 ; Resolve-DnsName atlas.lab | 389 open; atlas.lab answers | DC-Domain-Controllers/Build-Guide
| 4 | Media + VirtIO driver ISO ready | Windows Server 2025 ISO at the latest CU + the VirtIO/QEMU-guest-agent ISO attached to the VM. | (media) build + patch level ; VirtIO ISO mounted | current media + VirtIO ISO on hand | 220-Prepare-the-Ubuntu-Golden-Image (pattern) · Proxmox VirtIO
| 5 | Backup target online (PBS / BKP01) | The BKP01/PBS datastore is up for the post-build backup. | ping <bkp01> ; (PBS UI) | reachable; datastore online | BKP01 device page · ADR-0036
| 6 | Tier-1 admin credential ready | t1-seth (member-server admin) available — NOT Domain Admin (ADR-0024). | (Vaultwarden) t1-seth entry | Tier-1 cred on hand | ADR-0024 · 303 Part 5
1 · VM create & base OS | 7 | Create the VM on the planned host | a) placement per Service-Server-Build-Plan (EQR6 always-on / R410 spin-up); b) UEFI/OVMF, machine type q35; c) VirtIO SCSI disk + VirtIO NIC; d) attach the Windows ISO + the VirtIO ISO; e) enable the QEMU Guest Agent option. | (PVE) qm config <vmid> | VirtIO disk/net; agent=1; UEFI | Service-Server-Build-Plan · PVE01-Networking
| 8 | Install Windows Server 2025 | a) boot the Windows ISO; b) load the VirtIO storage driver so Setup sees the disk; c) Desktop Experience unless Core is chosen; d) set a strong local Administrator password (store in Vaultwarden — POL-0002). | Get-ComputerInfo ¦ Select WindowsProductName,OsVersion | Server 2025; current build | DC-Domain-Controllers/Build-Guide (Stage 1)
| 9 | Install VirtIO NIC driver + QEMU guest agent | From the VirtIO ISO: install the NIC driver + the QEMU guest agent; start & set the service to auto. | Get-Service QEMU-GA ; Get-NetAdapter ; (host) qm agent <vmid> ping | agent Running; VirtIO NIC bound; host ping OK | Playbooks/Proxmox-Inspect-and-Troubleshoot
| 10 | Snapshot clean-base-<date> | Before any config (VM Snapshot & Naming standard) — the rollback point. | (PVE) snapshot list | clean-base-<date> present | VM Snapshot & Naming standard
2 · Base OS configuration | 11 | Rename to the standard hostname | <ROLE##> per 303 naming (e.g. FS01, WSUS01, SQL01); reboot. | hostname ; Get-ComputerInfo ¦ Select CsName | correct hostname after reboot | 303 Part 2 (naming)
| 12 | Set the static IPv4 | Address / mask / gateway from IP-Addressing-Plan-VLSM on the role-VLAN interface. | Get-NetIPConfiguration | IP / mask / gw match the plan | IP-Addressing-Plan-VLSM
| 13 | Point DNS at the DCs | Primary 10.20.0.2, secondary 10.20.0.3 — never a public resolver on a domain member. | Get-DnsClientServerAddress | 10.20.0.2, 10.20.0.3 | ADR-0003 · DC Build-Guide (Stage 4)
| 14 | Timezone + High-performance power plan | a) Set-TimeZone -Id 'Central Standard Time'; b) set the High performance power plan (servers don't sleep). | Get-TimeZone ; powercfg /getactivescheme | CST; High performance | 303 Design Standards
| 15 | Activate Windows (licensing) | Activate via the decided method (KMS / MAK) — AVMA is Hyper-V-only, so it does NOT apply on Proxmox. | slmgr /dlv (or Get-CimInstance SoftwareLicensingProduct) | Licensed | 302 (licence clocks)
| 16 | Fully patch before joining | Windows Update to clean; reboot & repeat (an under-patched box is a rebuild risk). | Get-HotFix ¦ Sort InstalledOn -Desc ¦ Select -First 5 | latest CU installed | DC-Domain-Controllers/Build-Guide (Stage 1)
3 · Time & networking verify | 17 | 🔴 Disable hypervisor guest time-sync | A domain member takes time from the DOMHIER, not QEMU/CMOS (the ADR-0020 trap). Disable the QEMU guest-agent time sync for this VM. | w32tm /query /source (re-check after join) | a DC — not "VM IC Time" / "Local CMOS Clock" | ADR-0020 · Playbooks/Proxmox-Inspect-and-Troubleshoot
| 18 | Verify VLAN tag + gateway reach | The vNIC is on the role VLAN and the gateway answers. | Test-NetConnection <gw> -InformationLevel Detailed | reachable; 0% loss | Playbooks/Trace-a-Blocked-Flow
| 19 | Verify DNS resolution | Internal + external names resolve. | Resolve-DnsName atlas.lab ; Resolve-DnsName www.microsoft.com | both answer (internal from a DC) | ADR-0051 · Playbooks/Recover-from-a-DNS-Outage
4 · Security baseline & hardening | 20 | Windows Firewall on — all profiles | Domain / Private / Public enabled; default-deny inbound. | Get-NetFirewallProfile ¦ Select Name,Enabled | all Enabled = True | 303 Part 6
| 21 | Disable legacy protocols | SMBv1 off; LLMNR off; NetBIOS-over-TCP off. Full CIS/MS baseline lands by GPO after join. | Get-WindowsOptionalFeature -Online -FeatureName SMB1Protocol | SMB1 = Disabled | 303 Part 6
| 22 | Enable RDP for admin — NLA + scoped | a) enable RDP; b) require Network Level Auth; c) firewall-scope the RDP rule to PAW / mgmt only (not open). | (reg) fDenyTSConnections=0 ; UserAuthentication=1 | RDP on; NLA required; scoped | 303 Part 6 · PAW01
| 23 | Confirm Microsoft Defender active | Real-time protection on until the Server baseline GPO applies. | Get-MpComputerStatus ¦ Select RealTimeProtectionEnabled | True | 303 Part 6
5 · Domain join & identity | 24 | Join atlas.lab as a member server | Join with t1-seth; reboot. | Get-ComputerInfo ¦ Select CsDomain,CsDomainRole | atlas.lab / MemberServer | DC Build-Guide (Stage 8) · 303 Part 2
| 25 | Move object to Computers\Servers\<type> | The correct role OU (File-Print / App-Servers / Infra) — not the default Computers container. | (DC) Get-ADComputer <host> -Properties DistinguishedName | under Computers\Servers\... | 303 Part 3 (OU design)
| 26 | Confirm baseline GPOs applied | Baseline Server Security + LAPS from the Servers OU (303 Part 6). | gpresult /r /scope computer | Baseline Server + LAPS listed; no errors | GPO-Design-and-Build · 303 Part 6
| 27 | Confirm LAPS manages the local admin | Password present + rotating in AD; readable only by Tier-1. | (Tier-1) Get-LapsADPassword -Identity <host> | rotating managed password (Tier-2 denied) | GPO-Design-and-Build (LAPS) · ADR-0024
6 · Telemetry, backup & certificate | 28 | Ship logs / metrics to MON01 | Windows Event Forwarding + SNMP to the estate sink (Phase 6, LibreNMS). | (MON01) host in LibreNMS / WEF subscription active | host visible on MON01 | MON01 device page (#34)
| 29 | Set the managed update source | Point at WSUS01 (or the approved update ring) via GPO. | gpresult /r (WSUS policy) | managed update source set | WSUS01 device page
| 30 | Add to PBS / BKP01 backup + snapshot | Include the VM in the scheduled backup; take <role>-built-<date>. | (PBS) job includes VM ; (PVE) snapshot list | in the job; snapshot present | BKP01 device page · ADR-0013
| 31 | Machine cert via autoenrollment 📋 gated on PKI | Once AD CS / ICA01 is issuing — LDAPS / computer-auth cert (DC Stage-9 pattern). | certutil -pulse ; Get-ChildItem Cert:\LocalMachine\My | cert issued by Atlas Issuing CA | DC Build-Guide (Stage 9) · AD-CS guide
7 · Record & handoff | 32 | Paste read-backs into the Build-Record | POL-0001 evidence; create / patch Devices/<host>/Build-Record. | (doc) Devices/<host>/Build-Record | read-backs pasted | Templates/Build-Record-Template
| 33 | Add the host to NetBox 📋 if NetBox pending | The IPAM / DCIM source-of-truth entry + primary IP. | (NetBox) device + primary IP | recorded in NetBox | NETBOX01 device page