## PVE02 Commissioning
Atlas — New Proxmox Server Commissioning Checklist
Host: PVE02 (Beelink EQR6) · Lab-02-Cisco-Core · Virtualization — the low-power, always-on critical-tier hypervisor (ADR-0036).
Source: Build-Guides/221-PVE02-EQR6-Bring-Up + 201 (R410 prep) pattern + Devices/PVE02-Hypervisor. POL-0001: nothing is Done (✓) without the read-back.
HOW TO USE ▶ Fill in the yellow cells as you go: Done (✓) · Date · Who · Time · Notes/Evidence (→ the 📸 screenshot ref). Work top-to-bottom; each Phase-0 box gates the rest.
Row 9 (grey) is an EXAMPLE showing the expected format — overwrite or delete it. Never record a live secret (POL-0002).
Steps complete: | 0 / 24 steps done
Phase | # | Task | What to do | Verify (command) | Expected (healthy) | Done ✓ | Date | Who | Time | Notes / Evidence (📸)
1 · Hardware & BIOS | — | (example) Confirm RAM detected | overwrite or delete this row | free -h | ≈64 GiB | ✓ | 2026-08-05 | seth | 14:20 | 62 GiB seen; 📸 free-h.png
0 · Prerequisites gate (🔴 do not proceed until all checked) | 1 | EQR6 in hand with 64 GB RAM installed | 64 GB is the ADR-0036 prerequisite (unit ships 32 GB). | free -h | ≈ 62–64 GiB total
| 2 | 8 TB external attached & healthy | Hosts PBS + FS01 data (ADR-0036 v1.2). | lsblk ; smartctl -H /dev/sdX | disk present; SMART PASSED
| 3 | SW01 trunk port ready for PVE02 | New trunk: native 999, allowed 10–90,999, DAI-trusted (mirror Gi1/0/4). Owned by the SW01 page-set — add it there. | (SW01) show interfaces trunk ; show ip arp inspection | trunking 10–90,999, native 999, DAI-trusted
| 4 | BKP01 / PBS reachable with a datastore | The backup vehicle for the later VM migration. | ping <bkp01> ; (PBS UI) | reachable; datastore online
| 5 | Encrypted off-site copy path exists | ADR-0009/0013 — don't retire any R410 copy until off-site is confirmed. | (manual) off-site copy verified | confirmed
| 6 | DC02 (cold-standby) available | Needed later as fallback authority during the DC cutover. | (DC02) repadmin /replsummary | clean / 0 errors
1 · Hardware & BIOS | 7 | Record hardware + firmware inventory | Fill in Notes: model, CPU, RAM, NVMe/M.2, NIC count, BIOS version. | lscpu ; lsblk ; (BIOS) | recorded in Notes
| 8 | BIOS: enable virtualization + IOMMU | Enable AMD SVM (VT-x equiv) + IOMMU/VT-d; set correct date/time; keep boot mode consistent. | (BIOS) then egrep -c 'svm¦vmx' /proc/cpuinfo | > 0 after OS install
| 9 | Confirm RAM + storage detected | 64 GB seen; NVMe + M.2 healthy. | free -h ; lsblk | ≈64 GiB; disks present
| 10 | Note: EQR6 has NO iDRAC | Console = HDMI + keyboard at the unit (no remote OOB; no shared-LOM trap). | (informational) | n/a
2 · Proxmox install & host | 11 | Install Proxmox VE 8.x | Hostname pve02 / FQDN pve02.lab (standalone, .lab mgmt plane). | pveversion | pve-manager/8.x
| 12 | Switch to no-subscription repo + update | Convert enterprise→no-sub repo; apt update && apt full-upgrade; re-apply the no-sub widget patch. | apt update | no 401 enterprise-repo error
| 13 | Create named admin seth-admin@pve | PVE-realm named admin; scope root (206). 🔴 Proxmox is root-based — sudo is NOT installed; strip 'sudo' from external tutorials. | pveum user list | seth-admin@pve present; login works
| 14 | Set time to the ADR-0020 source | chrony/NTP → DC01 10.20.0.2. 🔴 Set BEFORE any DC is placed here (a wrong host clock just relocates CM-0012). | timedatectl ; chronyc sources | synchronized: yes; source 10.20.0.2
3 · Networking (mirror the PVE01 authoritative design — ADR-0034) | 15 | vmbr0 = VLAN-aware bridge | On the primary NIC; bridge-vids 10,20,30,40,50,60,70,80,90,999; NO L3 on bare vmbr0. | cat /etc/network/interfaces | vmbr0 vlan-aware, bridge-vids set
| 16 | vmbr0.10 = tagged VLAN-10 mgmt | 10.10.0.11/27 (📋 IP plan owns — deconflict vs WAC01 .5 / PAW); gateway 10.10.0.1. | ip -br address | vmbr0.10 = 10.10.0.11/27
| 17 | Verify the uplink carries the VM VLANs | 🔴 The bridge-vids trap: if the uplink isn't tagged for a VLAN, VM frames on it are silently dropped. | bridge vlan show | uplink tagged on 10–90,999
| 18 | Verify gateway reachability | From the EQR6 mgmt interface (vmbr0.10). | ping -c4 10.10.0.1 | 0% loss
| 19 | Confirm the SW01 side | PVE02 uplink = trunk, native 999, DAI-trusted (owned by the SW01 page-set). | (SW01) show interfaces trunk | native 999, allowed 10–90,999, DAI-trusted
4 · Storage | 20 | Keep local / local-lvm | Default PVE datastores. | pvesm status | local + local-lvm active
| 21 | Add the 8 TB external datastore | For PBS + the FS01 data disk (ADR-0036 v1.2). | pvesm status | the 8 TB store active
5 · Standalone & handoff | 22 | Stay standalone — join nothing | ADR-0046: a cluster is on-demand only (1 GbE / S2D caveat). | pvecm status | standalone (no cluster)
| 23 | Record all read-backs into the PVE02 Build-Record | POL-0001 evidence; #21 owns the device page-set. | (doc) Devices/PVE02-Hypervisor/Build-Record | read-backs pasted
| 24 | THEN: migrate the always-on tier per 221 | DC01→ICA01→NPS01→SRV01→Vaultwarden→FS01 via PBS restore (221 Phase 3–5) — a separate operation. | (see 221) | n/a — follow-on